## Budget
Line ID | Room | Category | Budget EUR | Committed EUR | Spent EUR | Variance EUR | Owner | Notes
BL-K01 | Kitchen | Cabinetry | 8900 | 8900 | 4450 | 4450 | Maria | Voutos accepted; 50% deposit paid
BL-K02 | Kitchen | Tiling | 3800 | 3800 | 2900 | 900 | Niko | kitchen share of the tiling quote
BL-K03 | Kitchen | Electrics | 2950 | 0 | 1000 | 1950 | Niko | Voltaris quote still pending
BL-K04 | Kitchen | Worktop (quartz) | 2100 | 0 | 0 | 2100 | Maria | StoneWorks pending
BL-K05 | Kitchen | Appliances | 2600 | 1450 | 1450 | 1150 | Niko | induction hob 60 vs 75cm undecided
BL-K06 | Kitchen | Paint + finishing | 380 | 380 | 380 | 0 | Maria | DIY, materials bought
BL-K07 | Kitchen | Plumbing (first fix) | 1270 | 1270 | 1150 | 120 | Niko | Demetriou first fix
BL-B01 | Bathroom | Plumbing (wetroom) | 2130 | 2130 | 0 | 2130 | Niko | Demetriou phase 2
BL-B02 | Bathroom | Tiling | 2400 | 2400 | 1900 | 500 | Niko | bathroom share of the tiling quote
BL-B03 | Bathroom | Sanitaryware | 1900 | 0 | 0 | 1900 | Maria | wall-hung WC + vanity not ordered
BL-B04 | Bathroom | Underfloor heating | 1450 | 0 | 0 | 1450 | Maria | options still being researched
BL-B05 | Bathroom | Shower screen / glazing | 1180 | 1180 | 400 | 780 | Maria | Kanellos Glazing, deposit paid
BL-B06 | Bathroom | Waterproofing (tanking) | 940 | 940 | 940 | 0 | Niko | tanking kit + primer
BL-H01 | Hallway | Skylight (hallway) | 1800 | 0 | 0 | 1800 | Maria | stretch item, only if contingency holds
BL-H02 | Hallway | Flooring (engineered oak) | 3640 | 3640 | 1200 | 2440 | Niko | Oikonomou Flooring
BL-X01 | Whole flat | Skip hire + waste | 760 | 760 | 620 | 140 | Niko | two skips booked
BL-X02 | Whole flat | Contingency | 4000 | 0 | 0 | 4000 | Both | drawdown ref CD-2026-XL7 - needs both to agree
TOTALS | - | - | 42200 | 26850 | 16390 | 25810 | - | workbook tag XLS-RENO-V7 (version 7, exported 2026-08-03)

## Quotes
Quote Ref | Contractor | Trade | Room | Amount EUR | Received | Valid Until | Status
Q-2210-GLAZE | Kanellos Glazing | Shower screen / glazing | Bathroom | 1180 | 2026-07-30 | 2026-09-30 | accepted
Q-2210-FLOOR | Oikonomou Flooring | Engineered oak flooring | Hallway | 3640 | 2026-07-31 | 2026-10-15 | accepted
Q-2211-SKY | Diaugis Skylights | Hallway skylight | Hallway | 1800 | 2026-08-01 | 2026-09-15 | on hold (stretch item)
Q-2211-WATER | Demetriou Plumbing | Wetroom tanking | Bathroom | 940 | 2026-08-01 | 2026-10-01 | accepted
Q-2207-CAB | Voutos Cabinetry | Cabinetry | Kitchen | 8900 | 2026-07-18 | 2026-09-18 | accepted
Q-2207-TILE | Hansson Tiling | Tiling (kitchen + bath) | Both | 6200 | 2026-07-19 | 2026-09-19 | accepted
Q-2207-PLUMB | Demetriou Plumbing | Plumbing | Both | 3400 | 2026-07-20 | 2026-09-20 | accepted
Q-2207-ELEC | Voltaris SA | Electrics | Kitchen | 2950 | 2026-07-21 | 2026-09-21 | pending
Q-2207-STONE | StoneWorks GR | Quartz worktop | Kitchen | 2100 | 2026-07-24 | 2026-09-24 | pending
Q-2210-HOB | Ilektro Domus | Induction hob + double oven | Kitchen | 1450 | 2026-07-29 | 2026-08-29 | accepted (60cm); 75cm quoted at 1,780
Q-2211-UFH | ThermoAttica | Electric underfloor heating | Bathroom | 1450 | 2026-08-02 | 2026-10-02 | comparing - see heating research
Q-2211-SKIP | Kallithea Skip Co | Skip hire (2 x 8yd) | Whole flat | 760 | 2026-07-25 | 2026-08-25 | accepted
Q-2211-BEAM | Voutos Cabinetry | Steel beam + padstone (variation) | Kitchen | 600 | 2026-08-02 | 2026-09-02 | pending - the load-bearing wall

## Expenses
Receipt Ref | Date | Payee | Trade | Room | Amount EUR | Method | Budget Line | Note
RC-0722-VA | 2026-07-22 | Voutos Cabinetry | Cabinetry | Kitchen | 4450 | bank transfer | BL-K01 | 50% deposit
RC-0725-SK | 2026-07-25 | Kallithea Skip Co | Waste | Whole flat | 320 | card | BL-X01 | first skip
RC-0728-HA | 2026-07-28 | Hansson Tiling | Tiling | Both | 4800 | bank transfer | BL-K02 | tile + adhesive materials
RC-0729-PA | 2026-07-29 | Chromata Paints | Paint | Kitchen | 380 | card | BL-K06 | RAL 1015 warm white, 3 x 10L
RC-0801-DE | 2026-08-01 | Demetriou Plumbing | Plumbing | Kitchen | 1150 | bank transfer | BL-K07 | first fix
RC-0802-VO | 2026-08-02 | Voltaris SA | Electrics | Kitchen | 1000 | bank transfer | BL-K03 | rough-in interim payment
RC-0803-KA | 2026-08-03 | Kanellos Glazing | Glazing | Bathroom | 400 | card | BL-B05 | shower-screen deposit
RC-0803-TA | 2026-08-03 | Domiki Materials | Waterproofing | Bathroom | 940 | card | BL-B06 | tanking kit + primer
RC-0804-OI | 2026-08-04 | Oikonomou Flooring | Flooring | Hallway | 1200 | bank transfer | BL-H02 | oak deposit
RC-0804-SK | 2026-08-04 | Kallithea Skip Co | Waste | Whole flat | 300 | card | BL-X01 | second skip (demolition week)
RC-0805-IL | 2026-08-05 | Ilektro Domus | Appliances | Kitchen | 1450 | card | BL-K05 | induction hob 60cm + double oven
RC-0806-HW | 2026-08-06 | Ergaleia Rent | Tools | Whole flat | 145 | card | BL-X01 | SDS breaker hire, 3 days

## Contractors
Contractor | Contact | Trade | Phone | Email | Quote Ref | On site from | Rating (1-5) | Notes
Voutos Cabinetry | Stefanos Voutos | Cabinetry | +30 210 555 4410 | stefanos@voutos-cab.gr | Q-2207-CAB | 2026-08-25 | 5 | flagged the load-bearing wall
Hansson Tiling | Astrid Hansson | Tiling | +30 210 555 9921 | astrid@hansson-tiling.gr | Q-2207-TILE | 2026-08-18 | 4 | only on site Tue-Thu
Demetriou Plumbing | Kostas Demetriou | Plumbing | +30 210 555 3377 | kostas@demetriou-plumb.gr | Q-2207-PLUMB | 2026-08-04 | 5 | also quoted the hot-water cylinder
Voltaris SA | Eleni Voltari | Electrics | +30 210 555 7712 | eleni@voltaris.gr | Q-2207-ELEC | 2026-08-04 | 3 | slow to confirm the quote
StoneWorks GR | Yiannis Petrou | Quartz worktop | +30 210 555 1180 | sales@stoneworks.gr | Q-2207-STONE | 2026-09-01 | 3 | template only after the cabinets land
Kanellos Glazing | Dimitra Kanellou | Shower screen / glazing | +30 210 555 8812 | dimitra@kanellos-glass.gr | Q-2210-GLAZE | 2026-10-05 | 4 | 10-week lead time on the screen
Oikonomou Flooring | Petros Oikonomou | Engineered oak flooring | +30 210 555 6034 | petros@oikonomou-floors.gr | Q-2210-FLOOR | 2026-10-12 | 4 | wants the underfloor heating in first
Ilektro Domus | Sofia Raptis | Appliances | +30 210 555 2299 | sofia@ilektrodomus.gr | Q-2210-HOB | 2026-09-08 | 4 | holds the 75cm hob until 2026-08-20
Diaugis Skylights | Marios Diaugis | Hallway skylight | +30 210 555 4477 | marios@diaugis.gr | Q-2211-SKY |  | 3 | stretch item, quote lapses 2026-09-15
Kallithea Skip Co | office | Waste / skips | +30 210 555 0090 | book@kallithea-skips.gr | Q-2211-SKIP | 2026-08-04 | 4 | 48h notice for a swap